## Slide 1: SGM Weekly Meeting
2022.10.07
Notes: Hi everyone. At this week's SGM meeting, I'll talk about the work we've completed and the upcoming plan

## Slide 2: Merge code with SLI
SLI’s code
SLT’s code
WORK-CENTER
Notes: Currently, we are in the process of merging the code with SLI, this process takes a long time and needs to be handled carefully.
It started yesterday and we expect it to finish on October 12th.
To do this, we come together and use Git as a support tool
Up to now, we have done 30% of this work and this work will be continued next week.

## Slide 3: Fix bugs & add new requirements
Fixed bugs
Customer management:
Download excel with customer data
Validate again Customer form Detail
Etc…
Employee management:
Fixed bug employee when searching click to icon
Ticket management:
Synchronized ticket status when user clicks to detail: Update from New to In-progress, etc…
Notes: Next, we continue to improve the management functions in Ticket, Customer, and Employee.
Some bugs occurred during the development of new features, so we fixed them in this week.
In Customer management: We fixed 3 bugs such as Download excel with customer data, Validate again Customer form Detail, and changing some messages in the alert.
In Employee management: We checked again when users click icon-search.
In Ticket management: We fixed 3 bugs

## Slide 4: Fix bugs & add new requirements
Update new requirements
Customer management:
Download excel template
Add more information to Customer Detail, etc…
Employee management:
Add more ways to add a new department.
Download, upload excel function, etc…
Ticket management:
Change flow getting Customer information in Ticket Detail when the customer has been not registered in the Database
Valid comment for the user when changing Ticket workflow, etc…
Notes: And this is one of the most important tasks of this week: Update new requirements and improve this system.
We updated 4 requirements in Customer such as Download excel template(it means without data), adding more information to Customer Detail and etc
We made more ways to add departments in the Employee management and made some Excel functions.
About Ticket management, it has a lot of new requirements to do, such as Changing flow getting Customer information in Ticket Detail when the customer has been not registered in the Database, and valid comment for the user when changing Ticket Workflow

## Slide 5: Weekly report 2022.10.04~2022.10.07
Planning for this week | Execution for this week | Planning for next week
Merge code with SLI in the Work-Center module Receive the Admin source code to evaluate & get the overall | Merged code with SLI in the Work-Center module(30%) | Finish merge code with SLI Testing after merge code Start merge code with VW after finishing merge code with SLI
Apply new requirements: 3 requirements in Customer 3 requirements in Employee | Apply new requirements: 4 requirements in Customer 3 requirements in Employee 5 requirements in Ticket | Receive the Admin source code to evaluate & get the overall Clearing SLT’s role in the Admin source code.
Fix bugs: Fix bugs in the Customer page Fix bugs in the Employee page | Fixed bugs: 3 bugs in the Customer page 1 bug in the Employee page 3 bugs in the Ticket page | Packaging, handling over, and finishing all parts on the Work-Center module
Notes: And this is my weekly report this week.
We focus on improving the Work-Center module, refactoring some code, and preparing for merge code with SLI
Now we are merging process. It’s completed about 30%
However, I didn't get the source code of the Admin module, As far as I know, we will receive this source code next week.
So after receiving this source code. We will clear SLT’s role in the Admin source code.
The main job for next week is to finish the merge code, test after the merge.
So, I will pack, and handling over the Work-Center module before I leave Korea.

## Slide 6: WBS
 | October |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | In-charge | Week 1 |  |  |  |  | Week 2 |  |  |  |  |  | Week 3 |  |  |  | 
 |  | 10.3 Mon | 10.4 Tue | 10.5 Wed | 10.6 Thu | 10.7 Fri | 10.10 Mon | 10.11 Tue | 10.12 Wed | 10.12 Wed | 10.13 Thu | 10.14 Fri | 10.17 Mon | 10.18 Tue | 10.19 Wed | 10.20 Thu | 10.21 Fri
2.5 version Admin | VW |  | Development |  |  |  |  | Test |  |  |  |  | Documentation |  |  |  | 
Brand Page Improvement | VW |  |  |  |  |  |  | Improvement |  |  | ◆ |  |  |  |  |  | 
2.5 version Work-Center | SLI |  | Development |  |  | Test |  | Test |  |  |  |  |  |  |  |  | 
Ticket, Customer, Staff Management | SLT |  | Development |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Source Integration (SLI/SLT) | SLI, SLT |  |  |  | Merge code |  |  | Merge code |  |  | Test |  |  |  |  |  | 
Source Integration (SLx/VW) | SLI, SLT, VW |  |  |  |  |  |  |  |  |  |  | Merge code |  |  |  |  | 
Notes: For the overall Work Breakdown Structure:
Now, VW is developing a 2.5 version of the Admin module during SLI development 2.5 version on the Work-Center module.
SLI and SLT are merging code on the Work Center.
VW also develop a Brand page on the Work-Center module. So after merging code between SLT and SLI, we will merge code with VW on the Work-Center
VW will write the Admin's document in the 3rd week of October.

## Slide 7: Timeline
Oct 20
Oct 12
NOW
Merge code SLT and SLI on the Work-Center module
Receive the documentation, requirements on the Admin module
Develop on the Admin module
Nov 1
Advance and improve on the Work-Center module
Develop new features on the Admin module
Testing after merge with SLI
Merge code with VW
Notes: It is the timeline for Saltlux
From now until Oct 12th, we will be done merging code with SLI
After that, we will test and confirm that all code is running correctly with the latest version before merging with VW.
From Oct 20, SLT will start developing the Admin module and may improve on the Work-Center module from Nov 1.

## Slide 8: Thank you!